## Features
# | Feature | Description | Release | State | Notes | 39
4 | GUI - Graphical Links | Lines drawn between multiple windows | 0 - Sandbox | Complete
2 | GUI - Image | Image contained in the window | 0 - Sandbox | Complete
1 | GUI - Movable Window | polygon that can be moved with the mouse | 0 - Sandbox | Complete
3 | GUI - Text | Text contained in the window | 0 - Sandbox | Complete
5 | GUI - Zoom | mouse wheel zoom on windows | 0 - Sandbox | Complete
11 | Browser - Chrome | ok | 1 - Proof of Concept | Complete | by design
7 | Data Source - Wikipedia | as a module | 1 - Proof of Concept | Partial | need more abstraction from UI module
10 | Flexible Object Model | design with multiple data sources, content types in mind | 1 - Proof of Concept | Partial | for simplicity, only Mediawiki supported sites will be used
13 | Hyperlinks - Internal | hyperlinks that we have data for should open up within the app | 1 - Proof of Concept | Complete
12 | Language - English | ok | 1 - Proof of Concept | Complete | by design
28 | Real-Time Parser | articles can be parsed in real-time, removing the need for a database | 1 - Proof of Concept | Complete
6 | Search | finds content that is supported by the app | 1 - Proof of Concept | Complete
9 | Tag/Link - Types | Tag, Parent/Child, bi-directional | 1 - Proof of Concept | Removed | for simplicity, only one link type will be used
15 | Database Server | talks to the app | 2 - Web Ready | Removed | real-time parser removes the need for a database
14 | Web Server | code hosted on a server, with external clients | 2 - Web Ready
18 | Auto Arrange | organize onscreen objects, eg by time | 3 - Eye Candy | Partial | Grid arrange
31 | Auto Arrange 1 | Create new window close to source window | 3 - Eye Candy | Complete
32 | Auto Arrange 2 | Create new window in unused space close to source window | 3 - Eye Candy | Complete
37 | Auto Arrange 3 | Apply zoom distances to spacing | 3 - Eye Candy
33 | Auto Arrange 4 | move other windows to create space for a new window | 3 - Eye Candy
34 | Auto Arrange 5 | proximity determined by link relevance | 3 - Eye Candy
22 | Data Source - Any Mediawiki | User can add an API to the search | 3 - Eye Candy | Partial | need more abstraction for API string
17 | Geo Tag | Allow objects to be linked to a geography | 3 - Eye Candy
29 | Load All Links | User can load a list of all links (i.e. in groups of 10), not limited to the most popular | 3 - Eye Candy
8 | Tag/Link - Resolution | Low relevance links will appear as you zoom in | 3 - Eye Candy
16 | Timescale | Allow objects to be linked to a timeline | 3 - Eye Candy
36 | Window Focus 1 | special attribute for a window under focus | 3 - Eye Candy
35 | Window Focus 2 | Linked window's size determined by relevance | 3 - Eye Candy
19 | Window Pin | Freeze the active window, eg does not zoom away | 3 - Eye Candy
20 | Tag/Link - Relevance Vote | user +/- on relevance of a link | 4 - User Account | Removed | fully rely on real-time parser, not users
21 | Tag/Link - User Generated | add a new link | 4 - User Account | Removed | users can create their own Mediawiki site
23 | Browser - FireFox | ok | 5 - Full Browser
24 | Browser - IE | ok | 5 - Full Browser
25 | Smart Search | Suggest other wikis | 6 - Data Sources
26 | Touchscreen | tbd | 7 - Touch
27 | Language - Other | tbd | 8 - Language | Partial | any Mediawiki site can be used
38 | Draggable background | ok | 3 - Eye Candy | Complete
39 | Triffic Analytics | Add Google Analytics | 2 - Web Ready

## Bugs-Tweaks
# | Bug/Tweak | Description | State | Notes
1 | Zoom Spacing | Space between windows is not maintained properly on zoom | open
2 | Zoom to Mouse | Zoom should centre the screen on the mouse location | open
3 | Drag background on Firefox | does not work | open | check event variable (pageX vs clientX)
4 | Enter button search | Enter button should execute the search (not refresh page) | partial | works while clicked inside the text box
5 | Background Drag does not refresh all links | … | open
6 | Zoom does not refresh all links | … | open
7 | Add external link to Wikipedia article | at the end of the summary section | Complete
8 | Filter out "coordinates" as a non-valid first paragraph | Articles with a coordinate will only show the lat/lon in the summary | Complete | ex: Hong Kong
9 | Filter out "Cite error: there are <ref> tags..." at the end of the summary | Some articles contain that sentence at the end of the summary | Complete | ex: Sound, Hat
10 | Some hyperlinks in the summary do not draw the line when clicked | … | open | ex: Bear -> Asia
11 | New windows should start in Display2 (image) when zoomed out | … | Complete | new windows start with links and summary closed
12 | Handle redirected articles | If an article has a redirect, open the redirect instead | Complete | ex: Audio Recording
13 | Browser window should not have scroll bars for off screen content | … | Complete
14 | Titles spill past the window when zoomed out | Wrap/split long words or shrink font | Complete
15 | Change mouse icon on background drag | … | Complete
16 | Dates < 1000 CE | do not sort | Complete
17 | Show common links | show all other articles common to 2 articles joined by a link | open
| check for existing article on Search | do not create a new article if it already exists (maybe centre the screen) | open
| centre on article | button

## MetaData
# | Genre | Field | Info Box text | List | State | Notes
1 | Music | Origin | Origin |  | Complete | city
2 | Music | Genres | Genres | y | Complete
3 | Music | Start Date | Years active |  | Complete
4 | Music | End Date | Years active |  | Complete
5 | Music | Labels | Labels | y | Complete
6 | Music | Members | Members | y | Complete
7 | Music | Past members | Past members | y | Complete
8 | Music | Associated acts | Associated acts | y | Complete
9 | Person | Start Date | Born |  | Complete
10 | Person | End Date | Died |  | Complete
11 | Person | Works | Notable work(s) | y | Complete
12 | Person | Field | Field | y | open | ex painting, sculpting
13 | Person | Genres | Movement | y | Complete
14 | Person | Genres | Style | y | Complete
| Movie | Members | Starring |  | Complete
| Movie | Directed By | Directed By |  | Complete
| Movie | Produced by | Produced by |  | Complete
| Movie | Start Date | Release Date |  | Complete
| Book | Author | Author |  | Complete
| Book | Start Date | Publication Date |  | Complete
| Book | Publisher | Publisher |  | Complete

## Date format
State
bday tag |  | ok
dday tag |  | ok
Month dd, yyyy | "April 15, 2011" | ok
| "before 31 October 1451" | ok | Christopher Columbus
| "31 October 1451" | ok
| "c. 1500" | ok | Marco Polo
| "20 May 1506 (aged c. 54)" | ok | Christopher Columbus
| "20 May 1506 City" | ok
| "20 May 1506, City" | ok
| "1254 city" | ok
| "ca. 1455" | ok | Filipa Moniz Perestrelo
| "20-21 May 1506 City" | ok | Marco Polo